## PP
Sovy - Digital Calculator PO1_DGC_PROJECT PLAN
PROJECT NAME | PROJECT MANAGER | START DATE | DELIVERY DATE | OVERALL PROGRESS | PROJECT DELIVERABLES
Sovy - Digital Calculator PO1_DGC | Hazem Mekawy | 2020-01-22 | February 22 , 2020 | 12.5% |  | asdasd | asdas
PROJECT CYRS LINK | https://docs.google.com/document/d/1FLBKHJtrkYKAzjZ1rkh2xkxFHRxZ_5YWzr9_X-QxBOc/edit?usp=sharing | [6 empty] | asddsdsdasd
TASK NAME | FEATURE TYPE | RESPONSIBLE | START DATE (EXPECTED) | END DATE (EXPECTED) | START DATE (ACTUAL) | END DATE (ACTUAL) | DURATION (DAYS) | STATUS | COMMENTS
PLANNING PHASE
WEEK 1
Project Plan | Non -Technical | Hazem Mekawy | 2020-01-22 | - | 2020-01-22 | - | - | ON GOING
SIQ Document Initiation | Non -Technical | Mina Helmi | 2020-01-23 | 2020-01-24 | 2020-01-23 | 2020-01-24 | 2 | DELIVERED | Commited SIQ
CYRS Document Initiation | Non -Technical | Nada Mohamed | 2020-01-22 | 2020-01-24 | 2020-01-22 | 2020-01-23 | 2 | DELIVERED | Commited CYRS v1.0
CYRS Document Initiation | Non -Technical | Alzahraa El-Sallakh | 2020-01-22 | 2020-01-24 | 2020-01-22 | 2020-01-23 | 2 | DELIVERED | Commited CYRS v1.0
HSI Document Initiation | Non -Technical | Esraa Awad | 2020-01-22 | 2020-01-24 | 2020-01-22 | 2020-01-23 | 2 | DELIVERED | Commited HSI v1.0
WEEK 2
SIQ Document Update | Non -Technical | Esraa Awad | 2020-02-03 | 2020-02-04 |  |  |  | STILL
CYRS Document Update | Non -Technical | Alzahraa El-Sallakh | 2020-02-04 | 2020-02-05 |  |  |  | STILL
CYRS Document Update Review | Non -Technical | Nada Mohamed | 2020-02-05 | 2020-02-06 |  |  |  | STILL
SRS Document Initiation & Update | Non -Technical | Mina Helmi | 2020-02-04 | 2020-02-05 |  |  |  | STILL
RTM Document Initiation & Update | Non -Technical | Hazem Mekawy | 2020-02-05 | 2020-02-06 |  |  |  | STILL
RTM Document Review | Non -Technical | Alzahraa El-Sallakh | 2020-02-06 | 2020-02-06 |  |  |  | STILL
SRS Document Review | Non -Technical | Hazem Mekawy | 2020-02-05 | 2020-02-06 |  |  |  | STILL
HSI Document Update | Non -Technical | Esraa Awad | 2020-02-04 | 2020-02-05 |  |  |  | STILL
HSI Document Update Review | Non -Technical | Nada Mohamed | 2020-02-05 | 2020-02-06 |  |  |  | STILL
WEEK 2 Review | Non -Technical | Hazem Mekawy | 2020-02-06 | 2020-02-07 |  |  |  | STILL
WEEK 3