## PP
Sovy - Digital Calculator PO1_DGC_PROJECT PLAN
PROJECT NAME | PROJECT MANAGER | START DATE | DELIVERY DATE | PROJECT DELIVERABLES
Sovy - Digital Calculator PO1_DGC | Hazem Mekawy | 2020-01-22 | 2020-03-20 |  | asdasd | asdas
PROJECT CYRS LINK | https://docs.google.com/document/d/1FLBKHJtrkYKAzjZ1rkh2xkxFHRxZ_5YWzr9_X-QxBOc/edit?usp=sharing | [6 empty] | asddsdsdasd
TASK NAME | TASK TYPE | RESPONSIBLE | START DATE (EXPECTED) | END DATE (EXPECTED) | START DATE (ACTUAL) | END DATE (ACTUAL) | DURATION (DAYS) | STATUS | COMMENTS
PLANNING PHASE
WEEK 1
Project Plan | Documentation | Hazem Mekawy | 2020-01-22 | - | 2020-01-22 | - | - | ON GOING
SIQ Document Initiation | Documentation | Mina Helmi | 2020-01-23 | 2020-01-24 | 2020-01-22 | 2020-01-23 | 2 | DELIVERED | Commited SIQ
CYRS Document Initiation | Documentation | Nada Mohamed | 2020-01-22 | 2020-01-24 | 2020-01-23 | 2020-01-24 | 2 | DELIVERED | Commited CYRS v1.0
CYRS Document Initiation | Documentation | Alzahraa El-Sallakh | 2020-01-22 | 2020-01-24 | 2020-01-23 | 2020-01-24 | 2 | DELIVERED | Commited CYRS v1.0
HSI Document Initiation | Documentation | Esraa Awad | 2020-01-22 | 2020-01-24 | 2020-01-23 | 2020-01-24 | 2 | DELIVERED | Commited HSI v1.0
WEEK 2
SIQ Document Update | Documentation | Esraa Awad | 2020-02-03 | 2020-02-04 | 2020-02-04 | 2020-02-05 | 2 | DELIVERED
CYRS Document Update | Documentation | Alzahraa El-Sallakh | 2020-02-04 | 2020-02-05 | 2020-02-04 | 2020-02-05 | 2 | DELIVERED
CYRS Document Update Review | Documentation | Nada Mohamed | 2020-02-05 | 2020-02-06 | 2020-02-05 | 2020-02-05 | 1 | DELIVERED
SRS Document Initiation & Update | Documentation | Mina Helmi | 2020-02-04 | 2020-02-05 | 2020-02-03 | 2020-02-05 | 3 | DELIVERED
SRS Document Review | Documentation | Hazem Mekawy | 2020-02-05 | 2020-02-06 | 2020-02-05 | 2020-02-06 | 2 | DELIVERED
RTM Document Initiation & Update | Documentation | Hazem Mekawy | 2020-02-05 | 2020-02-06 | 2020-02-06 | 2020-02-06 | 1 | DELIVERED
RTM Document Review | Documentation | Alzahraa El-Sallakh | 2020-02-06 | 2020-02-06 | 2020-02-06 | 2020-02-06 | 1 | DELIVERED
HSI Document Update | Documentation | Esraa Awad | 2020-02-04 | 2020-02-05 | 2020-02-04 | 2020-02-05 | 2 | DELIVERED
HSI Document Update Review | Documentation | Nada Mohamed | 2020-02-05 | 2020-02-06 | 2020-02-05 | 2020-02-06 | 2 | DELIVERED
WEEK 2 Review | Documentation | Hazem Mekawy | 2020-02-06 | 2020-02-07 | 2020-02-07 | 2020-02-07 | 1 | DELIVERED | Except the lastest review that was on 6/2/2020
WEEK 3
SIQ Document Update | Documentation | Nada Mohamed | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08 | 1 | DELIVERED
HSI Document Update | Documentation | Nada Mohamed | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08 | 1 | DELIVERED
Releasing CYRS/HSI Documents | Documentation | Hazem Mekawy | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08 | 1 | DELIVERED
SRS Document Update | Documentation | Mina Helmi | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08 | 1 | DELIVERED
WEEK 4
SRS Document Update | Documentation | Mina Helmi | 2020-02-22 | 2020-02-23 | 2020-02-22 | 2020-02-24 | 3 | DELIVERED
SRS Document Review | Documentation | Esraa Awad | 2020-02-23 | 2020-02-23 | 2020-02-24 | 2020-02-24 | 1 | DELIVERED
GDD Document Initiation | Documentation | Alzahraa El-Sallakh | 2020-02-24 | 2020-02-25 | 2020-02-24 | 2020-02-26 | 3 | DELIVERED
WEEK 4 (CRS Update Cycle)
CYRS Documuent Update | Documentation | Hazem Mekawy | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2 | DELIVERED | Updating the CYRS according to these changes: - Adding the clear switch separate from the keypad - Adding the new opearands limits
HSI Document Update | Documentation | Esraa Awad | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-27 | 1 | DELIVERED
SRS Document Update | Documentation | Mina Helmi | 2020-02-26 | 2020-02-27 | 2020-02-27 | 2020-02-27 | 1 | DELIVERED
GDD Document Update | Documentation | Alzahraa El-Sallakh | 2020-02-28 | 2020-02-28 | 2020-02-27 | 2020-02-27 | 1 | DELIVERED
RTM Document Update | Documentation | Hazem Mekawy | 2020-02-28 | 2020-02-28 | 2020-02-28 | - |  | STILL
WEEK 5
SRS Document Update | Documentation | Mina Helmi | 2020-03-01 | 2020-03-02 | 2020-03-02 | 2020-03-03 | 2 | DELIVERED | Please check the changes in the SRS review
GDD Document Update | Documentation | Alzahraa El-Sallakh | 2020-02-28 | 2020-02-28 | 2020-02-28 | 2020-02-28 | 1 | DELIVERED
CDD Document Initiation | Documentation | Nada Mohamed | 2020-03-01 | 2020-03-03 | 2020-03-03 | 2020-03-05 | 3 | DELIVERED | Creation of the CDD Document with assistance of Esraa
CDD Document Review | Documentation | Esraa Awad | 2020-03-03 | 2020-03-04 | 2020-03-04 | 2020-03-05 | 2 | DELIVERED | Assisting and reviewing Nada's work
RTM Document Update | Documentation | Hazem Mekawy | 2020-03-04 | 2020-03-05 | - | - |  | STILL
Releasing the Documents based on the documents reviews | Documentation | Hazem Mekawy | 2020-03-05 | 2020-03-05 | - | - |  | STILL
WEEK 6
SRS Document Update | Documentation | Mina Helmi | 2020-03-06 | 2020-03-07 |  |  |  | STILL | Add new requirements to cover the pins for each modules, you can aquire the data related to these requirements from the HSI document in the table of ports.
GDD Document Update | Documentation | Alzahraa El-Sallakh | 2020-03-06 | 2020-03-08 |  |  |  | ON GOING | Check the GDD Document review by date 5/3/2020
CDD Document Update | Documentation | Nada Mohamed | 2020-03-06 | 2020-03-08 |  |  |  | ON GOING | Update the CDD Document based on the lecture review 6/3/2020
HSI Document Update | Documentation | Esraa Awad | 2020-03-07 | 2020-03-07 |  |  |  | ON GOING | Update the HSI Document based on the lecture review 6/3/2020
Releasing the Documents based on the documents reviews | Documentation | Hazem Mekawy | 2020-03-08 | 2020-03-08 |  |  |  | STILL
RTM Document Update | Documentation | Hazem Mekawy | 2020-03-08 | 2020-03-09 |  |  |  | STILL