## CYRS review
Date | Reviewer | Document | Review point | Acceptance | Point status | Comment
27/1/2020 | Ali | CYRS | Missing document status history section it shall be a table with the following coloms --> "Version, Date , Auther,Status " to monitor the doc. Status through many versions, yes you provide the version and the status in the first table but that's the final result a status history is needed as a separate section | Accepted | Closed | Mali 3/2/2020: Point is reviewed and closed
28/1/2020 | Ali | CYRS | In requirement Req_PO1_DGC_CYRS_005_V01 the ON/OFF operation is done using 2 switches while in SIQ sheet it's just one switch | Accepted | Closed | Mali 3/2/2020: Point is reviewed and closed
2020-03-02 | Ali | CYRS | In requirement Req_PO1_DGC_CYRS_005_V01 : Remove this part " If the LCD is off" | Accepted | Open
2020-03-02 | Ali | CYRS | Document still in PDF format also Status still drat while it should be proposed as it's under review now | Accepted | Open

## HSI review
Date | Reviewer | Document | Review point | Acceptance | Point status | Comment
27/1/2021 | Ali | HSI | Missing document status history section it shall be a table with the following coloms --> "Version, Date , Auther,Status " to monitor the doc. Status through many versions, yes you provide the version and the status in the first table but that's the final result a status history is needed as a separate section | Accepted | Closed | Mali 3/2/2020: Point is reviewed and closed
27/1/2022 | Ali | HSI | All requirement IDs in HSI are defind with CYRS document name not HSI. Ex: Req_PO1_DGC_CYRS_001_V01 this shall be Req_PO1_DGC_HSI_001_V01 | Accepted | Closed | Mali 3/2/2020: Point is reviewed and closed
2020-03-02 | Ali | HSI | Document still in PDF format also Status still drat while it should be proposed as it's under review now |  | Open
2020-03-02 | Ali | HSI | In 1.2 version change history add the following comment "Fixing HSI requirement by replacing CYRS with HSI" |  | Open