## CYRS review
Date | Reviewer | Document | Review point | Point status | Comment
27/1/2020 | Ali | CYRS | Missing document status history section it shall be a table with the following coloms --> "Version, Date , Auther,Status " to monitor the doc. Status through many versions, yes you provide the version and the status in the first table but that's the final result a status history is needed as a separate section | Open
28/1/2021 | Ali | CYRS | In requirement Req_PO1_DGC_CYRS_005_V01 the ON/OFF operation is done using 2 switches while in SIQ sheet it's just one switch | Open

## HSI review
Date | Reviewer | Document | Review point | Point status | Comment
27/1/2021 | Ali | HSI | Missing document status history section it shall be a table with the following coloms --> "Version, Date , Auther,Status " to monitor the doc. Status through many versions, yes you provide the version and the status in the first table but that's the final result a status history is needed as a separate section | Open
27/1/2022 | Ali | HSI | All requirement IDs in HSI are defind with CYRS document name not HSI. Ex: Req_PO1_DGC_CYRS_001_V01 this shall be Req_PO1_DGC_HSI_001_V01 | Open