## SRS review
Date | Reviewer | Document | Review point | Acceptance | Point status | Comment
2020-06-02 | Ali | SRS | Please provide a requirement to delace that SW shall detect the pressed key from the keypad | Accepted | Closed | Added a new reuirement Req_PO1_DGC_SRS_012_V01 for this point.
2020-06-02 | Ali | SRS | Req_PO1_DGC_SRS_006_V01: Shall divided to 2 requirements also "The software shall check the operator <Operator> and the second operand <Opr2>" isn't a complete requirement | Accepted | Closed | Changed the statement to be more explicit and clear. The requirement cannot be divided into 2 requirements, since it's only concerned with a division by zero operation.
2020-06-02 | Ali | SRS | Req_PO1_DGC_SRS_010_V01 is same as requirement "Req_PO1_DGC_SRS_007_V01" | Accepted | Closed | Removed requirement Req_PO1_DGC_SRS_010_V01, and appended the useful parts to requirement Req_PO1_DGC_SRS_007_V01
2020-06-02 | Ali | SRS | Req_PO1_DGC_SRS_011_V01 & Req_PO1_DGC_SRS_012_V01 requirement doesn't declare the previos state when the switch is pressed | Accepted | Closed | Added the desired previous state of the switch in each requirement.
2020-06-02 | Ali | SRS | State machine is wrong and has no requirement ID | Rejected | Closed | Renamed the State Machine to Flow Chart and added a new reuirement Req_PO1_DGC_SRS_013_V01 to explicitely state that the software design should follow the described flow chart .
13/2/2020 | Ali | SRS | Tones that will be sent to buzzer aren't defined, For example the tone signal is DC signal or PWM and if it's PWM what's the duty and freq. for it? | Accepted | Closed | Updated the requirements Req_PO1_DGC_SRS_004_V01 and Req_PO1_DGC_SRS_005_V01 to reflect the new requirements.
13/2/2020 | Ali | SRS | Cur_x and Cur_y are not defined with specific values, developer shall know the exact values for them | Accepted | Closed | Added 4 new requirements Req_PO1_DGC_SRS_014_V01, Req_PO1_DGC_SRS_015_V01, Req_PO1_DGC_SRS_016_V01 and Req_PO1_DGC_SRS_017_V01 to indicate the ranges of the horizontal and vertical cursor positions and what should happen if they were exceeded Mali 19/2/2020: I didn't mean that, I meant for example Req_PO1_DGC_SRS_009_V01 the requirement shall mention the value of x and y Mina 20/02/2020: The values cannot be mentioned exactly/explicitly since they're a range. But the requirements Req_PO1_DGC_SRS_014_V01 and Req_PO1_DGC_SRS_016_V01 were updated to be more descriptive.
24/2/2020 | Ali | SRS | Move SRS context under project description |  | Open
24/2/2020 | Ali | SRS | SRS context shall not has a req_ID remove it's presence form SRS_013, alos inputs and outputs have no meaning for this requirement |  | Open