## PP
Sovy - Digital Calculator PO1_DGC_PROJECT PLAN
PROJECT NAME | PROJECT MANAGER | START DATE | DELIVERY DATE | OVERALL PROGRESS | PROJECT DELIVERABLES
Sovy - Digital Calculator PO1_DGC | Hazem Mekawy | 2020-01-22 | - | - |  | asdasd | asdas
PROJECT CYRS LINK | https://docs.google.com/document/d/1FLBKHJtrkYKAzjZ1rkh2xkxFHRxZ_5YWzr9_X-QxBOc/edit?usp=sharing | [6 empty] | asddsdsdasd
TASK NAME | TASK TYPE | RESPONSIBLE | START DATE (EXPECTED) | END DATE (EXPECTED) | START DATE (ACTUAL) | END DATE (ACTUAL) | DURATION (DAYS) | STATUS | COMMENTS
PLANNING PHASE
WEEK 1
Project Plan | Documentation | Hazem Mekawy | 2020-01-22 | - | 2020-01-22 | - | - | ON GOING
SIQ Document Initiation | Documentation | Mina Helmi | 2020-01-23 | 2020-01-24 | 2020-01-22 | 2020-01-23 | 2 | DELIVERED | Commited SIQ
CYRS Document Initiation | Documentation | Nada Mohamed | 2020-01-22 | 2020-01-24 | 2020-01-23 | 2020-01-24 | 2 | DELIVERED | Commited CYRS v1.0
CYRS Document Initiation | Documentation | Alzahraa El-Sallakh | 2020-01-22 | 2020-01-24 | 2020-01-23 | 2020-01-24 | 2 | DELIVERED | Commited CYRS v1.0
HSI Document Initiation | Documentation | Esraa Awad | 2020-01-22 | 2020-01-24 | 2020-01-23 | 2020-01-24 | 2 | DELIVERED | Commited HSI v1.0
WEEK 2
SIQ Document Update | Documentation | Esraa Awad | 2020-02-03 | 2020-02-04 | 2020-02-04 | 2020-02-05 | 2 | DELIVERED
CYRS Document Update | Documentation | Alzahraa El-Sallakh | 2020-02-04 | 2020-02-05 | 2020-02-04 | 2020-02-05 | 2 | DELIVERED
CYRS Document Update Review | Documentation | Nada Mohamed | 2020-02-05 | 2020-02-06 | 2020-02-05 | 2020-02-05 | 1 | DELIVERED
SRS Document Initiation & Update | Documentation | Mina Helmi | 2020-02-04 | 2020-02-05 | 2020-02-03 | 2020-02-05 | 3 | DELIVERED
SRS Document Review | Documentation | Hazem Mekawy | 2020-02-05 | 2020-02-06 | 2020-02-05 | 2020-02-06 | 2 | DELIVERED
RTM Document Initiation & Update | Documentation | Hazem Mekawy | 2020-02-05 | 2020-02-06 | 2020-02-06 | 2020-02-06 | 1 | DELIVERED
RTM Document Review | Documentation | Alzahraa El-Sallakh | 2020-02-06 | 2020-02-06 | 2020-02-06 | 2020-02-06 | 1 | DELIVERED
HSI Document Update | Documentation | Esraa Awad | 2020-02-04 | 2020-02-05 | 2020-02-04 | 2020-02-05 | 2 | DELIVERED
HSI Document Update Review | Documentation | Nada Mohamed | 2020-02-05 | 2020-02-06 | 2020-02-05 | 2020-02-06 | 2 | DELIVERED
WEEK 2 Review | Documentation | Hazem Mekawy | 2020-02-06 | 2020-02-07 | 2020-02-07 | 2020-02-07 | 1 | DELIVERED | Except the lastest review that was on 6/2/2020
WEEK 3
SIQ Document Update | Documentation | Nada Mohamed | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08 | 1 | DELIVERED
HSI Document Update | Documentation | Nada Mohamed | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08 | 1 | DELIVERED
Releasing CYRS/HSI Documents | Documentation | Hazem Mekawy | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08 | 1 | DELIVERED
SRS Document Update | Documentation | Mina Helmi | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08 | 1 | DELIVERED
WEEK 4
SRS Document Update | Documentation | Mina Helmi | 2020-02-22 | 2020-02-23 | 2020-02-22 | 2020-02-24 | 3 | DELIVERED
SRS Document Review | Documentation | Esraa Awad | 2020-02-23 | 2020-02-23 | 2020-02-24 | 2020-02-24 | 1 | DELIVERED
GDD Document Initiation | Documentation | Alzahraa El-Sallakh | 2020-02-24 | 2020-02-25 | 2020-02-24 | 2020-02-26 | 3 | DELIVERED
WEEK 4 (CRS Update Cycle)
CYRS Documuent Update | Documentation | Hazem Mekawy | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2 | DELIVERED | Updating the CYRS according to these changes: - Adding the clear switch separate from the keypad - Adding the new opearands limits
HSI Document Update | Documentation | Esraa Awad | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-27 | 1 | DELIVERED
SRS Document Update | Documentation | Mina Helmi | 2020-02-26 | 2020-02-27 | 2020-02-27 | 2020-02-27 | 1 | DELIVERED
GDD Document Update | Documentation | Alzahraa El-Sallakh | 2020-02-28 | 2020-02-28 | 2020-02-27 | 2020-02-27 | 1 | DELIVERED
RTM Document Update | Documentation | Hazem Mekawy | 2020-02-28 | 2020-02-28 | 2020-02-28 | - |  | ON GOING
WEEK 5
SRS Document Update | Documentation | Mina Helmi | 2020-03-01 | 2020-03-02 |  |  |  | ON GOING | Please check the changes in the SRS review
GDD Document Update | Documentation | Alzahraa El-Sallakh | 2020-02-28 | 2020-02-28 | 2020-02-28 | 2020-02-28 | 1 | DELIVERED
CDD Document Initiation | Documentation | Nada Mohamed | 2020-03-01 | 2020-03-03 |  |  |  | STILL | Creation of the CDD Document with assistance of Esraa
CDD Document Review | Documentation | Esraa Awad | 2020-03-03 | 2020-03-04 |  |  |  | STILL | Assisting and reviewing Nada's work
RTM Document Update | Documentation | Hazem Mekawy | 2020-03-04 | 2020-03-05 |  | - |  | STILL
Releasing the Documents based on the documents reviews | Documentation | Hazem Mekawy | 2020-03-05 | 2020-03-05 |  |  |  | STILL